## Financials
Month | Actual Realization ($) | Planned Investment ($) | Budget remaining | Budget Used(%) | Budget remaining (%) | Achievement (%) | Variance ($) | Variance (%) | Notes
2024-01-31 | 40000000 | 50000000 | 860000000 | 4.444% | 95.56% | 80% | -10000000 | -20% | Delay in equipment procurement
2024-02-28 | 40000000 | 50000000 | 820000000 | 8.889% | 91.11% | 80% | -10000000 | -20% | Delay in equipment procurement
2024-03-31 | 40000000 | 50000000 | 780000000 | 13.33% | 86.67% | 80% | -10000000 | -20% | Delay in equipment procurement
2024-04-30 | 60000000 | 75000000 | 720000000 | 20% | 80% | 80% | -15000000 | -20%
2024-05-31 | 70000000 | 75000000 | 650000000 | 27.78% | 72.22% | 93.33% | -5000000 | -6.667%
2024-06-30 | 50000000 | 50000000 | 600000000 | 33.33% | 66.67% | 100% | 0 | 0% | Progress as planned
2024-07-31 | 70000000 | 100000000 | 530000000 | 41.11% | 58.89% | 70% | -30000000 | -30% | Land acquisition issue
2024-08-31 | 70000000 | 100000000 | 460000000 | 48.89% | 51.11% | 70% | -30000000 | -30% | Land acquisition issue
2024-09-30 | 50000000 | 50000000 | 410000000 | 54.44% | 45.56% | 100% | 0 | 0%
2024-10-31 | 105000000 | 100000000 | 305000000 | 66.11% | 33.89% | 105% | 5000000 | 5% | EPC acceleration
2024-11-30 | 100000000 | 100000000 | 205000000 | 77.22% | 22.78% | 100% | 0 | 0% | EPC acceleration
2024-12-31 | 105000000 | 100000000 | 100000000 | 88.89% | 11.11% | 105% | 5000000 | 5% | EPC acceleration

## Schedule&Dependencies
Activity | Duration (weeks) | Start (Planned) | End (Planned) | Dependency | Progress Status | % Complete | Critical Path (Y/N)
FS | 4 | Jan W1 | Jan W4 | - | Completed | 100% | N
FEED | 8 | Feb W1 | Mar W4 | FS | Completed | 100% | Y
Procurement | 10 | Apr W1 | Jun W2 | FEED | Ongoing | 50% | Y
Civil | 12 | Apr W1 | Jun W4 | FEED | Ongoing | 40% | Y
Installation | 8 | Jul W1 | Aug W4 | Procurement, Civil | Not started | 0% | Y
Commissioning | 6 | Sep W1 | Oct W2 | Installation | Not started | 0% | Y

## Risk Register
Risk ID | Risk Description | Affected Activity | Quarter | Probability (H/M/L) | Impact (H/M/L) | Status | Mitigation Action
R1 | Delay in equipment procurement | Procurement | Q1 | High | High | Open | Engage multiple vendors
R2 | Land acquisition issue | Civil Works | Q3 | Medium | High | Open | Escalation to Gov’t taskforce
R3 | Compressed commissioning | Commissioning | Q4 | Medium | Medium | At Risk | Parallel testing, add QA team

## Milestone Tracking
Milestone | Planned Date | Actual/Forecast Date | Status (On Time/Delayed/At Risk) | Dependency | Strategic Impact
FS Completed | Jan W4 | Jan W4 | On Time | - | Feasibility done
FEED Completed | Mar W4 | Mar W4 | On Time | FS | Design ready
Procurement Completed | Jun W2 | Jul W1 | Delayed | FEED | Equipment mobilization
Civil Works Completed | Jun W4 | Jul W2 | Delayed | FEED | Site readiness
Installation Completed | Aug W4 | TBD | Not Started | Procurement, Civil | Key equipment installed
Commissioning Completed | Oct W2 | TBD | Not Started | Installation | First Euro IV fuel output

## Schedule
Activity | Predecessor(s) | ES | EF | LS | LF | Float | Critical? | StartDate_Planned | EndDate_Planned | Duration_Planned_days | StartDate_Actual | EndDate_Actual | Duration_Actual_days | % Completion as of Today | % Remaining as of Today | Notes
FS | – | 0 | 30 | 0 | 30 | 0 | Critical | 2024-02-19 | 2024-03-19 | 30 | 2024-02-19 | 2024-03-19 | 30 | 100% | 0%
FEED | FS | 30 | 84 | 30 | 84 | 0 | Critical | 2024-03-20 | 2024-05-12 | 54 | 2024-03-20 | 2024-05-12 | 54 | 100% | 0%
Procurement | FEED | 84 | 154 | 98 | 168 | 14 | Non-Crit | 2024-05-13 | 2024-07-21 | 70 | 2024-05-13 | 2024-09-30 | 140 | 100% | 0% | procurement
Civil | FEED | 84 | 168 | 84 | 168 | 0 | Critical | 2024-05-13 | 2024-08-04 | 84 | 2024-05-13 | 2024-11-25 | 196 | 92.86% | 7.143% | land
Installation | Procurement,Civil | 168 | 226 | 168 | 226 | 0 | Critical | 2024-08-05 | 2024-10-01 | 58 | 2024-11-26 | 2025-01-05 | 41 | 0% | 100% | epc
Commissioning | Installation | 226 | 272 | 226 | 272 | 0 | Critical | 2024-10-02 | 2024-11-16 | 46 | 2025-01-06 | 2025-02-16 | 42 | 0% | 100% | epc
Formulas:
StartDate_Planned = [EndDate_Planned, row above]+1
StartDate_Actual = [EndDate_Actual, row above]+1
EndDate_Actual = [StartDate_Actual]+[Duration_Actual_days]